## City
|  |  |  | Cut 1 |  | Cut 2 |  |  | Cut 3 |  |  | Cut 4 |  |  | Cut 5 |  |  | Cut 6
GMO | Area | Status | Freq (wks) | Completed | Freq | Completed | Due | Freq | Completed | Due | Freq | Completed | Due | Freq | Completed | Due | Freq | Completed | Due
North | Mackworth | Ahead | 8 | 2026-03-23 | 7.4286 | 2026-05-14 | 2026-05-18 | -6593.7143 |  | 2026-07-09 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
North | Markeaton Park | On Track | 8 | 2026-03-24 | 6.4286 | 2026-05-08 | 2026-05-19 | -6592.8571 |  | 2026-07-03 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
North | Allestree | Ahead | 8 | 2026-03-31 | 7.4286 | 2026-05-22 | 2026-05-26 | -6594.8571 |  | 2026-07-17 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
North | West End | Ahead | 8 | 2026-04-23 |  | 2026-06-12 | 2026-06-18 | -6597.8571 |  | 2026-08-07 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
North | Darley | Ahead | 8 | 2026-04-09 |  | 2026-06-01 | 2026-06-04 | -6596.2857 |  | 2026-07-27 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
North | Chester Green | Ahead | 8 | 2026-04-09 |  | 2026-06-01 | 2026-06-04 | -6596.2857 |  | 2026-07-27 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
North | Chaddesden | Behind | 8 | 2026-04-23 |  | 2026-06-24 | 2026-06-18 | -6599.5714 |  | 2026-08-19 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
North | Spondon | On Track | 8 | 2026-05-08 |  |  | 2026-07-03 |  |  | 1900-02-24 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
North | Oakwood | Behind | 8 | 2026-04-30 |  |  | 2026-06-25 | 0 |  | 1900-02-24 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Arboretum | Ahead | 8 | 2026-03-11 | 6.2857 | 2026-04-24 | 2026-05-06 | 5.5714 | 2026-06-02 | 2026-06-19 | -6596.4286 |  | 2026-07-28 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | City Centre | Ahead | 8 | 2026-03-12 | 5.7143 | 2026-04-21 | 2026-05-07 | 6.1429 | 2026-06-03 | 2026-06-16 | -6596.5714 |  | 2026-07-29 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Normanton | Ahead | 8 | 2026-03-13 | 5.7143 | 2026-04-22 | 2026-05-08 | 7.2857 | 2026-06-12 | 2026-06-17 | -6597.8571 |  | 2026-08-07 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Abbey Ward | Ahead | 8 | 2026-03-17 | 5.1429 | 2026-04-22 | 2026-05-12 | 7.2857 | 2026-06-12 | 2026-06-17 | -6597.8571 |  | 2026-08-07 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Littleover | Ahead | 8 | 2026-03-25 | 7.2857 | 2026-05-15 | 2026-05-20 | -6593.8571 |  | 2026-07-10 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Mickleover | Ahead | 8 | 2026-03-23 | 7 | 2026-05-11 | 2026-05-18 | 6 | 2026-06-22 | 2026-07-06 | -6599.2857 |  | 2026-08-17 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Blagreaves | Behind | 8 | 2026-03-20 | 5.8571 | 2026-04-30 | 2026-05-15 | -6591.7143 |  | 2026-06-25 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Sinfin/Osmaston | Ahead | 8 | 2026-03-27 | 7 | 2026-05-15 | 2026-05-22 | -6593.8571 |  | 2026-07-10 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Chellaston | Ahead | 8 | 2026-04-06 | 6.5714 | 2026-05-22 | 2026-06-01 | -6594.8571 |  | 2026-07-17 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Alvaston | Ahead | 8 | 2026-04-20 |  | 2026-06-08 | 2026-06-15 | -6597.2857 |  | 2026-08-03 |  |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
South | Boulton | Ahead | 8 | 2026-04-09 |  | 2026-05-28 | 2026-06-04 | -6595.7143 |  | 2026-07-23 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24 | 0 |  | 1900-02-24
|  | *Each 'Due' date will be set 8 weeks from the last completed cut. |  |  | 6.4881 |  |  | -4510.8647 |  |  | -3298.8 |  |  | 0 |  |  | 0
*The above schedule is for grass verge and small open space mowing only.
Formulas:
Due = [Cut 1]+D3*7

## South (hidden)
|  |  |  | Cut 1 |  | Cut 2 |  | Cut 3 |  | Cut 4 |  | Cut 5 |  | Cut 6
Area | Frequency (wks) | Ward | # | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due
Bass Rec | 8 | Arboretum | 1 | 2025-03-21 |  | 2025-04-25 | 2025-05-16
Arboretum Park | 3 | Arboretum | 1
City Centre | 8 | City Centre | 2 | 2025-03-21 |  | 2025-04-25 | 2025-05-16
River gardens | 1 | City Centre | 2
Normanton | 8 | Normanton | 3 | 2025-03-21 |  | 2025-04-25 | 2025-05-16
Normanton park | 8 | Normanton | 3 | 2025-03-21 |  | 2025-04-25 | 2025-05-16
Kenilworth ave/ Sinfin lane/ Sinfin rec/ Wordsworth | 8 | Normanton | 3 | 2025-03-28 |  | 2025-05-09 | 2025-05-23
Caxton park/ Qualcast park | 8 | Normanton | 3 | 2025-03-28 |  | 2025-05-09 | 2025-05-23
Rowditch | 8 | Abbey Ward | 4 | 2025-03-21 |  | 2025-04-25 | 2025-05-16
Rykneld | 8 | Abbey Ward | 4 | 2025-03-21 |  | 2025-04-25 | 2025-05-16
Stockbrook | 8 | Abbey Ward | 4 | 2025-03-21 |  | 2025-04-25 | 2025-05-16
Uttoxeter Road/Kingsway | 8 | Abbey Ward | 4 | 2025-03-28 |  | 2025-04-25 | 2025-05-23
Manor road/ Warwick ave | 8 | Abbey Ward | 4 | 2025-03-28 |  | 2025-05-02 | 2025-05-23
Abby/Lonsdale place | 3 | Abbey Ward | 4 | 2025-04-11 |  |  | 2025-05-02
Derby royal/ rough Heanor | 8 | Littleover | 5 | 2025-03-28 |  | 2025-04-25 | 2025-05-23
Chainlane | 8 | Littleover | 5 | 2025-03-28 |  | 2025-05-02 | 2025-05-23
Haven Baulk/ Rykneld road/ Pastures hill/ burton Road | 8 | Littleover | 5 | 2025-03-28 |  | 2025-05-09 | 2025-05-23
Western Road/ station road | 8 | Mickleover | 6 | 2025-03-28 |  |  | 2025-05-23
Lady bank/ Brierfield Way | 8 | Mickleover | 6 | 2025-03-28 |  |  | 2025-05-23
Catterick/ Vicarage | 8 | Mickleover | 6 | 2025-03-28 |  |  | 2025-05-23
Valley road/ Littleover bowls club | 8 | Blagreaves | 7 | 2025-03-28 |  | 2025-05-02 | 2025-05-23
King George | 8 | Blagreaves | 7 | 2025-04-04 |  |  | 2025-05-30
Blagraves | 8 | Blagreaves | 7 | 2025-04-04 |  |  | 2025-05-30
Stenson Green | 8 | Blagreaves | 7 | 2025-04-04 |  |  | 2025-05-30
The Chase | 8 | Sinfin | 8 | 2025-04-04 |  |  | 2025-05-30
Arkle green | 8 | Sinfin | 8 | 2025-04-04 |  |  | 2025-05-30
Merlin green | 8 | Sinfin | 8 | 2025-04-04 |  |  | 2025-05-30
Grampian | 8 | Sinfin | 8 | 2025-04-04 |  |  | 2025-05-30
Islay/ carron close | 8 | Sinfin | 8 | 2025-04-04 |  |  | 2025-05-30
Bird estate | 8 | Sinfin | 8 | 2025-04-04 |  |  | 2025-05-30
Osmaston park | 8 | Sinfin | 8 | 2025-04-04 |  |  | 2025-05-30
Osmaston park road | 8 | Sinfin | 8 | 2025-04-04 |  |  | 2025-05-30
Wilmore road | 8 | Sinfin | 8 | 2025-04-04 |  |  | 2025-05-30
Sinfin ave | 8 | Chellaston | 9 | 2025-04-04 |  |  | 2025-05-30
Backlane | 8 | Chellaston | 9 | 2025-04-11 |  |  | 2025-06-06
Infinity way | 8 | Chellaston | 9 | 2025-04-11 |  |  | 2025-06-06
Cordelia | 8 | Chellaston | 9 | 2025-04-11 |  |  | 2025-06-06
Chellaston east | 8 | Chellaston | 9 | 2025-04-11 |  |  | 2025-06-06
Fellow lands | 8 | Chellaston | 9 | 2025-04-11 |  |  | 2025-06-06
Chellaston Rec | 8 | Chellaston | 9 | 2025-04-11 |  |  | 2025-06-06
Courtway cres | 8 | Chellaston | 9 | 2025-04-11 |  |  | 2025-06-06
Pride park islands | 2 | Alvaston | 10 | 2025-04-18 |  |  | 2025-05-02
Keldholme | 8 | Alvaston | 10 | 2025-04-18 |  |  | 2025-06-13
Baker street allotments | 8 | Alvaston | 10 | 2025-04-18 |  |  | 2025-06-13
Alvo shops/tesco | 8 | Alvaston | 10 | 2025-04-18 |  |  | 2025-06-13
Kiwi drive + "woods" | 8 | Alvaston | 10 | 2025-04-18 |  |  | 2025-06-13
Lidl/McDonalds Raynesway | 8 | Alvaston | 10 | 2025-04-18 |  |  | 2025-06-13
Kiwi canal path | 8 | Alvaston | 10 | 2025-04-18 |  |  | 2025-06-13
Willmorton | 8 | Alvaston | 10 | 2025-04-18 |  |  | 2025-06-13
Boulton lane canal path | 8 | Boulton | 11 | 2025-04-11 |  |  | 2025-06-06
Boulton lane islands | 8 | Boulton | 11 | 2025-04-11 |  |  | 2025-06-06
Pylon | 8 | Boulton | 11 | 2025-04-11 |  |  | 2025-06-06
Cornishman | 8 | Boulton | 11 | 2025-04-11 |  |  | 2025-06-06
Field lane/ Wilmington | 8 | Boulton | 11 | 2025-04-11 |  |  | 2025-06-06
Chello shops/library | 8 | Chellaston | 12 | 2025-04-11 |  |  | 2025-06-06
Formulas:
Due = [Cut 1]+[Frequency (wks)]*7

## South (old) (hidden)
Area | Frequency (wks) | Ward | Cut 1 | Cut 2 | Cut 3 | Cut 4 | Cut 5 | Cut 6
· Bass Rec | 8 | Arboretum | Cut 1: 17/3/25 – 21/3/25; Cut 2: 21/4/25 – 25/4/25
· City Centre | 8 | city centre | bar: Cut 1 to Cut 2
· Arbo | 2 to 3 | Arboretum | bar: Cut 1 to Cut 2
· Normanton | 8 | Normanton | bar: Cut 1 to Cut 2
· Normanton park | 8 | Normanton | bar: Cut 1 to Cut 2
· Rowditch | 8 | Abbey Ward | bar: Cut 1 to Cut 2
· Rykneld | 8 | Abbey Ward | bar: Cut 1 to Cut 2
· Stockbrook | 8 | Abbey Ward | bar: Cut 1 to Cut 2
· Uttoxeter Road/Kingsway | 8 | Abbey Ward | Cut 1: 24/03/2025 - 28/03/2025
· Derby royal/ rough Heanor | 8 | Littleover | bar: Cut 1 to Cut 2
· Chainlane | 8 | Littleover | Cut 2: 28/4/24 – 2/5/25
· Manor road/ Warwick ave | 8 | Abbey Ward | bar: Cut 1 to Cut 2
· Western Road/ station road | 8 | Mickleover | bar: Cut 1 to Cut 2
· Lady bank/ Brierfield Way | 8 | Mickleover | bar: Cut 1 to Cut 2
· Catterick/ Vicarage | 8 | Mickleover | bar: Cut 1 to Cut 2
· Valley road/ Littleover bowls club | 8 | Blagreaves | bar: Cut 1 to Cut 2
· Haven Baulk/ Rykneld road/ Pastures hill/ burton Road | 8 | Littleover | Cut 2: 6/5/25 - 9/5/25
· Kenilworth ave/ Sinfin lane/ Sinfin rec/ Wordsworth | 8 | Normanton | bar: Cut 1 to Cut 2
· Caxton park/ Qualcast park | 8 | Normanton | bar: Cut 1 to Cut 2
· The Chase | 8 | Sinfin | Cut 1: 31/3/25 – 4/4/24
· Arkle green | 8 | Sinfin
· King George | 8 | Blagreaves
· Blagraves | 8 | Blagreaves
· Merlin green | 8 | Sinfin
· Grampian | 8 | Sinfin
· Stenson Green | 8 | Blagreaves
· Islay/ carron close | 8 | Sinfin
· Bird estate | 8 | Sinfin
· Osmaston park | 8 | Sinfin
· Osmaston park road | 8 | Sinfin
· Wilmore road | 8 | Sinfin
· Sinfin ave | 8 | Chellaston
· Backlane | 8 | Chellaston | Cut 1: 7/4/24 – 11/4/25
· Infinity way | 8 | Chellaston
· Cordelia | 8 | Chellaston
· Chellaston east | 8 | Chellaston
· Fellow lands | 8 | Chellaston
· Pride park islands | 2 | Alvaston
· Arbo | 2 to 3 | Arboretum
· River gardens | 1 | City Centre
· Chellaston Rec | 8 | Chellaston
· Courtway cres | 8 | Chellaston
· Boulton lane canal path | 8 | Boulton
· Boulton lane islands | 8 | Boulton
· Pylon | 8 | Boulton
· Cornishman | 8 | Boulton
· Field lane/ Wilmington | 8 | Boulton
· Abby/Lonsdale place | 3 | Abbey Ward
· Chello shops/library | 8 | Chellaston
· Keldholme | 8 | Alvaston | Cut 1: 14/4/25 – 18/4/25
· Baker street allotments | 8 | Alvaston
· Alvo shops/tesco | 8 | Alvaston
· Kiwi drive + "woods" | 8 | Alvaston
· Lidl/McDonalds Raynesway | 8 | Alvaston
· Kiwi canal path | 8 | Alvaston
· Willmorton | 8 | Alvaston
· Arbo | 2 to 3 | Arboretum | Cut 1: 21/4/25 – 25/4/25
· Riverlife footpath | 8 | Alvaston
· Alvo park | 8 | Alvaston
· Harvey road (zero turn)_ | 3 | Alvaston
· Cotton lane | 8 | Alvaston
· Pride park | 8 | Alvaston
Pride park islands | 2 to 3 | Alvaston | Cut 2: 2025-09-05

## Play Parks (hidden)
Park Name | March | April | May | June | July | August | September | October
Alvaston Park
Mowbray
Keldholme
Elvaston Lane
Rykneld
Stockbrook
Fullens Lock
Rowditch | March: 2026-04-02
Sinfin Rec
Chellaston Rec
Back Lane
Courtway Crescent | March: 2026-04-02
Duchess Way | March: 2026-04-02
King George
Havenbaulk
Boulton Lane
Bramblebrook
Osmaston
Sherwood Rec
Vicarage Road Rec
Shakespeare
Caxton/Sunny Hill
Normanton
Kiwi Canal
Sinfin Moor
Arkle Green
Aviemore Way
Swallowdale M.U.P.A
Ballater Close
Foxdale
Chellaston East
Field Lane | March: 2026-03-30
Cricket cage Normanton
Cordelia Way | March: 2026-04-02
Alvaston Rec | March: 2026-03-31
NOTE: This is a record for the back up works, parks will be mowed when verge teams get there.
* Mowed not by Verge team